## ISD
NOTE: proof of interaction with customers is mandatory and must be submitted frequently to show how much your customers involve in your project
Week no | Time | Task | Deliverable | Note
1
| 2023-06-02 | Student list
2 | 20/2 | Customer | Proof of customer existance | Paper-based documents, screenshot, pictures or scanned version of customers' documents such as invoice, contract
|  |  | Proof of interaction with customers | Email,mesenger, skype, records, etc
|  |  | Customer Persona | Use persona template on LMS
3 | 27/2 | Project description. | Project description | MS word file, free style
|  |  | General requirements | Usecase diagram
FIRST ITERATION
4 | 6/3 | First sprint planing | Sprint plan
|  | Daily meeting | What have been done (regarding User story, GUI and DB design, code, test plan, test cases, demonstration) Customer feedback? What to do next? Issues?
5 | 13/3 | Daily meeting | What have been done since last meeting(regarding user story, GUI and DB design, code, test plan, test cases, demonstration) Customer feedback? What to do next? Issues?
|  | Report on your customer meeting | Agenda, MOM | Also add evidence of meeting with customer (records, pictures, etc)
6 | 20/3 | Daily meeting | What have been done since last meeting(regarding user story, GUI and DB design, code, test plan, test cases, demonstration) Customer feedback? What to do next? Issues?
|  | Report on your customer meeting | Agenda, MOM | Also add evidence of meeting with customer (records, pictures, etc)
7 | 27/3 | Sprint demonstration | First working version and demonstration script | How do your customers involve in the projects? How to get feedback from customers (face to face, surveys…=> evidences)?
|  | Customer review and feedback for the first version | Feedback in details
|  | Retrospective meeting | Issues and how to improve
SECOND ITERATION
8
9 | 21/3 - 27/3 | Midterm Test
10 | 28/3 - 3/4
11 | 4/4 - 10/4
THIRD ITERATION
12 | 11/4 - 17/4
13 | 18/4 - 24/4
14 | 25/4 - 8/5